## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | swetha | 2025-05-12 | Initial speech recognition accuracy for Hindi audio was lower compared to English due to variations in pronunciation and accent. | Sprint-1 | swetha | Model Accuracy | Improved audio preprocessing and validated input quality before ASR inference using Whisper. | 2025-10-12 | Closed | Noticed improvement in Hindi transcription accuracy
2 | Priyanshi Raina | 2025-07-12 | Audio uploaded via microphone was recorded but not saved correctly, resulting in no transcription output. | Sprint-1 | Priyanshi Raina | Logical | Fixed audio save logic, added preprocessing, updated API response to return translated audio path, and connected frontend audio player dynamically. | 20-12-2025 | Closed | Recorded audio is now preprocessed and saved correctly
3 | swetha | 14-12-2025 | Initial evaluation only considered overall transcription quality and did not reflect language-wise performance differences. | Sprint-2 | swetha | Analytical | Implemented separate validation for English and Hindi outputs to better assess multilingual performance. | 18-12-2025 | Closed | Language-wise evaluation accuracy improved
4 | Etikala Akhila | 2025-03-12 | Backend implementation needed proper structure to handle audio processing, translation, and TTS workflow efficiently. | Sprint-1 | Etikala Akhila | Maintainability | Designed and implemented a structured Flask backend using Whisper for ASR, Google Translator for translation, gTTS for speech output, and FFmpeg for audio preprocessing. | 20-12-2025 | Closed | Backend working correctly as expected
5 | Konijeti Gayathri | 25-12-2025 | Original text was not generated for video uploads because audio was not extracted properly. | Sprint-3 | Konijeti Gayathri | Logical | Integrated FFmpeg-based audio extraction to convert video files into WAV format before transcription. | 30-12-2025 | Closed | Video input working correctly after FFmpeg integration
6 | Anjali Kumari | 25-12-2025 | Initial documentation lacked clarity on system workflow and module-level integration. | Sprint-3 | Anjali Kumari | Documentation / Functional Clarity | Reorganized and updated documentation with clear module-wise explanation, workflow diagrams, and detailed ASR–Translation–TTS pipeline description. | 28-12-2025 | Closed | Documentation clarity improved for team and mentor
7 | Priyanshi Raina | 2026-03-01 | Deployment attempt failed due to high memory usage and model incompatibility with cloud environment. | Sprint-4 | Priyanshi Raina | Environment | Decision taken to keep the project running locally and optimize inference instead of deploying. | 2026-05-01 | Closed | Project finalized as localhost due to high RAM dependency
8 | Konijeti Gayathri | 23-12-2025 | System initially supported only audio input and lacked support for video and YouTube URLs. | Sprint-2 | Konijeti Gayathri | Logical | Added separate pipelines for audio, video, and YouTube inputs using FFmpeg and yt-dlp; re-tested complete workflow. | 2026-02-01 | Closed | System works correctly for audio, video, and YouTube inputs

## Sheet2
Logical
User Interface
Maintainability
Standards
Others